## Sheet1
Task | Days | Concurrent? | Critical?
System Specification | 1
Test Plan | 4
Designing User Interface | 4
Designing Data Structres | 5
Designing Program Structure | 10
Implementation | 20
Alpha Testing | 10
Beta Testing | 6
Evaluation | 2
Documentation | 1
Task v
|  |  | Days > | 27/02/2018 - Tuesday | 2018-02-28 | 2018-03-01 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 25 | 27 | 29 | 31 | 2018-04-02 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | Completion Date | Actual date
System Specification
Test Plan | bar: 3 to 5
Designing User Interface | bar: 7 to 11
Designing Data Structres | bar: 9 to 15
Designing Program Structure | bar: 7 to 15
Implementation | bar: 17 to 31
Alpha Testing | bar: 27 to 31
Beta Testing
Evaluation
Documentation