## Sheet1
Task | Days | Concurrent? | Critical?
System Specification | 1
Test Plan | 4
Designing User Interface | 4
Designing Data Structres | 5
Designing Program Structure | 10
Implementation | 20
Alpha Testing | 10
Beta Testing | 6
Evaluation | 2
Documentation | 1
Task v
|  |  | Days > | 27/02/2018 - Tuesday | 2018-02-28 | 2018-03-01 | 3 | 5 | 7 | 9 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 25 | 27 | 29 | 31 | 2018-04-02 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | Completion Date | Actual date
|  |  |  | System Specification | [27 empty] | 28th Feb | 29th Feb
|  |  |  | Test Plan | [27 empty] | 5th Mar | 6th Mar | bar: 3 to 5
|  |  |  | Designing User Interface | [27 empty] | 11th Mar | 11th Mar | bar: 7 to 11
|  |  |  | Designing Data Structres | [27 empty] | 15th Mar | 15th Mar | bar: 9 to 15
|  |  |  | Designing Program Structure | [27 empty] | 15th Mar | 15th Mar | bar: 7 to 15
|  |  |  | Implementation | [27 empty] | 6th Apr | 12th Apr | bar: 17 to 31
|  |  |  | Alpha Testing | [27 empty] | 6th Apr | 14th Apr | bar: 27 to 31
|  |  |  | Beta Testing | [27 empty] | 14th Apr | 16th Apr
|  |  |  | Evaluation | [27 empty] | 18th Apr | 19th Apr
|  |  |  | Documentation | [27 empty] | 20th Apr | 24th Apr